## Launch Checklist
# | Priority | Action Item | Why It's Needed | Status
1 | Critical | Fix order confirmation email (switch to Brevo) | Render's free tier blocks SMTP (Gmail/Nodemailer) - live customers currently receive no order confirmation email | Pending
2 | Critical | Fix stock deduction bug | Stock is not automatically reduced when an order is placed, risking overselling | Pending
3 | Critical | Add real products to the database | Only 5 dummy/seed products exist currently; no real inventory is live | Pending
4 | Critical | Upgrade Render to a paid plan | Free tier has a 30-60 second cold-start delay after inactivity, which hurts real customer experience | Pending
5 | Critical | Integrate a payment gateway (e.g. Razorpay) | Only Cash on Delivery is available; Card/UPI customers are currently unable to pay online | Pending
6 | Important | Remove hardcoded reviews/discount data | 4.8/5.0 (200+ Reviews) and SAVE 10% currently show identically on every product regardless of real data - a trust risk | Pending
7 | Important | Purchase and connect a custom domain (e.g. coverly.in) | Site currently runs on the default coverly-nine.vercel.app address instead of a branded domain | Pending
8 | Important | Confirm support email is real and monitored | Legal pages reference support@coverly.in as the contact address | Pending
9 | Important | Confirm GST / business compliance with a CA | India e-commerce may have registration, invoicing, or tax obligations depending on turnover | Pending
10 | Nice-to-have | Build coupon/discount code system | Useful for future marketing campaigns (Instagram promos, festive sales) | Queued
11 | Nice-to-have | Build a real customer review system | Would replace the hardcoded review numbers with genuine customer feedback | Queued
12 | Nice-to-have | Add WhatsApp support integration | Common expectation for Indian D2C customers | Queued
13 | Nice-to-have | Add error monitoring (e.g. Sentry) | Helps catch and diagnose production issues proactively | Queued
14 | Nice-to-have | Fix image sizes prop warnings | Minor performance/optimization warnings seen in the browser console | Queued